PELLIKART

Mobile App — Project Plan, Requirements, Tech Stack & Costs

iOS & Android apps replicating the Pellikart web platform

Prepared by Nihanth  ·  July 2026

# 1. Objective

Bring the full Pellikart experience (pellikart.com) to native iOS and Android apps with complete feature parity with the current web application, while keeping the UI visually identical. The apps will reuse the existing Supabase backend, so web and mobile share one database, one matching algorithm, and one source of truth. The admin panel remains web-only — it already exists and is used on laptops, so rebuilding it on mobile adds cost without value.

# 2. Scope & Requirements

The list below consolidates the original requirements sheet, with recommended additions marked (NEW). Additions close gaps that would otherwise surface during development or app store review.

## 2.1 Client (Couple) App

- Onboarding: couple's names, current location (GPS), event planning, event dates via calendar, guest count, and budget.

- Matching algorithm suggesting vendors by location proximity, budget, guest count, and date — computed on the backend so web and mobile always return identical results.

- Vendor discovery with filters; UI kept visually identical to the web app.

- Tiered paywall for vendor names/contact details — 2 vendor names free, more revealed with paid tiers (see Section 3 for how this works on mobile).

- Vendor booking with UPI payment gateway; booking amount is 10% of the total quoted amount.

- Two-way milestone tracking between client and vendor.

- Reviews (NEW: restricted to completed bookings only, to prevent spam and protect vendor trust).

- Bundled vendor services with discounts.

- Venue visit / menu tasting requests, sent from the same subscription number.

- NEW: Phone OTP login (with WhatsApp OTP option — cheaper per message and better delivery in India).

- NEW: Push notifications: booking confirmations, milestone updates, visit-request responses.

- NEW: Clear refund & cancellation policy for the 10% booking amount (required by the payment gateway and both app stores).

- NEW: In-app callback/chat channel after booking, so client–vendor conversations stay on the platform (reduces off-platform settling that bypasses the 10% commission).

## 2.2 Vendor App

- Profile: business name, vendor category, base location (with current-location option), phone, email, Instagram, description, years of experience, team size.

- Listing flows identical to the web app, with different question sets per vendor category — built as configuration-driven forms so categories and questions can change without an app update.

- Self-onboarding routes to the admin panel for review; vendors appear on the platform only after approval.

- Availability calendar: block one or multiple listings for a custom range or full day; blocked listings are hidden from clients on those dates (enforced on the backend so web and mobile never drift).

- Reviews dashboard with all reviews and rating parameters.

- Menu tasting / visit requests: approve or propose a new time.

- Vendor analytics and booking management (cancelled, upcoming, completed).

- NEW: Push notifications for new leads, booking updates, and visit requests — a major reason vendors will prefer the app over the website.

- NEW: Vendor KYC during onboarding review (required by the payment gateway for automatic vendor payouts).

- NEW: Defined payout flow: Razorpay Route (split settlement) recommended so vendors are paid automatically instead of via manual transfers.

## 2.3 Admin Panel (remains web-only)

- Analytics: clients onboarded, vendors onboarded.

- Watch-tower view of client–vendor matches and bookings.

- Vendor onboarding review queue and approvals.

- Vendor onboarding codes created through the admin panel.

- NEW: Review moderation and milestone dispute visibility.

# 3. Payments & App Store Compliance (Important)

Apple and Google treat the two payment flows in the plan very differently, and this shapes the product:

- Vendor booking (10% of total): this is payment for a real-world service, so both stores allow our own UPI gateway (Razorpay) inside the app with no store commission.

- Paying to unlock vendor names: the stores classify this as a digital unlock. If sold inside the app, Apple and Google require their own billing systems and take 15–30% of every purchase.

Decision: unlock tiers are sold on the web app only (pellikart.com). The mobile apps simply recognise what the user has already purchased and show unlocked vendors accordingly — the same model Netflix and Spotify use. This keeps 100% of paywall revenue with Pellikart. One rule comes with it: the iOS app must not link to or mention purchasing on the website; locked vendors simply appear locked. Purchases sync to the app instantly via the shared backend.

# 4. Technology Stack

The web app is React-based and already runs on Supabase, so the stack below maximises reuse: one codebase produces both the iOS and Android apps, and shares code, types, and business logic with the existing website.

| Layer | Technology | Why |
| --- | --- | --- |
| Mobile framework | React Native + Expo | One codebase for iOS and Android; reuses React skills and code from the web app; over-the-air updates let us ship fixes without waiting for app store review. |
| Backend | Supabase (existing) | Same database, auth, storage, and APIs as the website — no second backend to build or keep in sync. |
| Matching & proximity | Postgres + PostGIS (in Supabase) | Location-proximity matching computed in the database — free, fast, and identical across web and mobile. |
| Payments (bookings) | Razorpay (UPI) | In-app UPI collection for the 10% booking amount; Razorpay Route for automatic vendor payouts. |
| Paywall entitlements | Web checkout + shared backend | Unlocks purchased on pellikart.com; apps read entitlements in real time. |
| Login | Phone OTP via MSG91 (SMS/WhatsApp) | Standard for the Indian market; WhatsApp OTP lowers cost and improves delivery. |
| Push notifications | Expo Push / Firebase Cloud Messaging | Free; drives repeat engagement for both clients and vendors. |
| Maps & location | Google Maps SDK | Map display and current-location capture; free tier covers early usage. |
| Crash & analytics | Sentry + PostHog | Crash reporting and product analytics; free tiers at our scale. |
| Builds & release | Expo EAS + App Store / Play Console | Managed cloud builds and store submission. |

# 5. Build Plan & Timeline

Development is in-house. The plan below targets full feature parity in roughly 3 to 3.5 months, with both apps submitted to the stores at the end. The two heaviest items are the category-specific vendor listing flows and the availability-calendar logic.

| Phase | Weeks | Deliverables |
| --- | --- | --- |
| 1. Foundation | 1–2 | Project setup, shared code structure with the web app, phone OTP login, navigation, and the design system ported so the apps match the website visually. |
| 2. Client side | 3–6 | Client onboarding, matching results, filters, locked/unlocked vendor cards, vendor details, reviews, visit & tasting requests. |
| 3. Vendor side | 7–9 | Vendor profiles, category-specific listing flows, availability calendar with listing blocking, reviews dashboard, analytics, booking management. |
| 4. Money & notifications | 10–11 | Razorpay booking flow, paywall entitlement sync, milestone tracking, push notifications across all events. |
| 5. Polish & launch | 12–14 | Offline / poor-network handling, crash reporting, store assets, review submissions to Apple and Google, launch. |

## Store submission notes

- Google Play: new personal developer accounts must run a closed test with 12 testers for 14 continuous days before public release — tester recruitment starts early, or we register an organisation account to avoid it.

- Apple: requires an in-app account-deletion option (built into scope) and demo logins for client, vendor, and a pre-seeded booking for their reviewer.

- Both stores require a public privacy policy and terms of service URL.

- First Apple review typically takes 1–3 days; the timeline includes buffer for one rejection cycle.

# 6. Pricing

## 6.1 One-time costs

| Item | Cost |
| --- | --- |
| Google Play developer account | US $25 (one-time) |
| Apple Developer Program | US $99 / year |

## 6.2 Monthly infrastructure

| Item | Cost | Notes |
| --- | --- | --- |
| Supabase Pro | US $25 / month | Needed as usage grows across web + two apps (database, auth, vendor photo storage). |
| Expo EAS builds | Free tier initially; US $19 / month later | Upgrade only when build volume demands it. |
| Sentry + PostHog | Free tiers | Sufficient at launch scale. |
| Google Maps API | Free tier | Proximity matching runs in our own database, keeping Maps usage minimal. |
| Estimated total | ≈ ₹2,500–4,500 / month | Until meaningful scale; grows with usage, not headcount. |

## 6.3 Per-transaction costs

| Item | Cost | Notes |
| --- | --- | --- |
| Razorpay (booking payments) | ≈ 2% per transaction | UPI rates are negotiable once volume builds; worth revisiting quarterly. |
| SMS / WhatsApp OTP (MSG91) | ≈ ₹0.15–0.20 per OTP | WhatsApp OTP is the cheaper channel. |
| App store commission on paywall | 0% | Avoided entirely by selling unlocks on the web (Section 3) — versus 15–30% if sold in-app. |

Summary: fixed costs are approximately US $99/year plus US $25 one-time for store accounts, and roughly ₹2,500–4,500 per month in infrastructure. Development is in-house, so the primary investment is engineering time over the ~14-week build.

# 7. Decisions Needed from You

- Refund & cancellation policy for the 10% booking amount (full refund window? sliding scale by days before the event?).

- Paywall tier pricing on the web (how many vendor reveals per tier, and at what price points).

- Milestone definitions for two-way tracking — which milestones, and who confirms each (client, vendor, or both).

- Vendor payout schedule — instant on booking via Razorpay Route, or held until a milestone/event completion.

- Google Play account type — organisation account (recommended; avoids the 14-day closed-testing requirement) or personal.

- Whether the post-booking chat/callback channel (Section 2.1) is in scope for v1 or a fast-follow.